## Sheet1
Task | Description | Time Req'd | Due Date | Task Dependencies |  | 14th Feb
1 | Replace DWN Firewall | 1day |  | 2
1a | Configure BSD 4.5 | 4hrs |  | 1c
1b | Analyse current config | 4hrs
1c | Install BSD 4.5 | 20min |  | Prefferably 1d
1d | Attach FW to Network | 20min |  | 2
2 | Install New Server | 1day |  | 6 & 3
2a | Physical Install | 1hr |  | 2e & 3
2b | Configure ESX Hosts | 2hrs |  | 2c
2c | Install ESX Hosts | 1hr |  | 2d
2d | Configure Storage System | 1hr |  | 2e
2e | Build New Server | 2hrs |  | 6
3 | Travel to Darwin | 4hrs |  | 2c
4 | Replace DWN MX | 1.5days | TBA | 1 & 2
4a | Copy Existing Users across | 8hrs |  | 4b & 4c
4b | Analyse current config | 2hrs
4c | Build New VM Server | 2hrs |  | 2 & Possibly 4d
4d | Discuss Flattening DOM
5 | Replace DWN TS/DC/FS | 2days | TBA | 1 & 2
5a | Geoff to install progs | 1day |  | 5b
5b | Configure VM Servers | 2hrs |  | 5d
5c | Analyse current config | 2hrs
5d | Build New VM Servers | 2hrs |  | 2
6 | Hardware Arrival | 3weeks |  |  |  | 3 Weeks
6a | Hardware Shipping | 3weeks |  | 6b
6b | Hardware Order | DONE | 14th Feb |  | u
7 | Existing FW Decom |  | Shane To Advise |  |  |  | u