## Sheet1
Date: | 2010-07-15 |  | Time: | 19:30-22:30
Duration: | 3hrs |  | Incident Number: |  | MS-008
Description of the Incident
Firewall outage. As the primary connection to the WAN from Data Centre, this outage caused the absolute loss of connection to critical systems, inlcuding domain controllers, web, dealer connections, external mail provider.
Reason/Cause
Prior to this outage, firewall was in a "ReadOnly" state, due to inconsistencies in the state of its harddrive. This put the firewall in a state where it could no longer service incoming mail from external mail provider. Some other services were affected.
Corrective Action taken to Resolve the problem
Firewall was rebooted a number of times. A) to determine if boot would repair issue, B) to reproduce issue and C) finally repair issue. Disk inconsistencies repaired with "fsck -y" command running in single user mode. NOTE: Corrective Action Caused Outage
Steps taken to reduce the chance of a recurrence
to reduce the chance of recurrence the firewall was moved to ESX host 2, with no other machines on this host. By isolating this server, we will reduce impact on other systems, be able to bring it back up if it fails and reserve more resources to it, reducing the chance of failure.
Any on-going actions required as a result
Shane and myself are in discussions as how to best solve this issue and are formulating business cases for these solutions.
Form completed By: |  | Michael Spence
Follow-up:-
Report back to:
Incident closed By: |  | Michael Spence |  | Date: | 2010-07-15
Attachments: