## Sheet1
Date: | 2010-07-28 |  | Time: | 11:00-12:30
Duration: | 1.5 hrs |  | Incident Number: |  | MS-009
Description of the Incident
Users could not access file shares and critical systems such as databases for registration programs or Banking systems.
Reason/Cause
Newsteaddc was in a crashed state and was non-responsive to remote management, RDP or onsite console. Network interface was still alive and was still pingable. Event log after restoration gave no clues to reason behind this crash, although I suspect a possible dropped disk from the RAID (needs verification).
Corrective Action taken to Resolve the problem
File server was visited and attempts were made to do a graceful shutdown. As the console was not accessible, a HARD reset was performed on ths system. When server was back on-line, system integrity was verified.
Steps taken to reduce the chance of a recurrence
This file server is well out of warranty and requires decommissioning. The new file server is being provisioned and dealerships are currently in the process of being moved to this new server.
Any on-going actions required as a result
Continue with transition to new file server NSD-FS1.
Form completed By: |  | Michael Spence
Follow-up:-
Report back to:
Incident closed By: |  | Michael Spence |  | Date: | 2010-07-28
Attachments: